## Summary
H200 Inference Platform — Decision Matrix
One row per decision point. Fill yellow cells (Owner, Required By, Decision/Notes, Status) in the Decision Matrix tab. Status counts below update automatically.
Status Tracker
Status | Count
Open | 66
In Progress | 0
Decided | 0
Deferred | 0
Total decisions | 66
Decision Tiers (sequencing)
1 - Blocks sizing | Resolve first: workload definition (1.x), data classification (7.1), facility power/cooling (8.1-8.3), decision ownership (11.4)
2 - Blocks quoting | Resolve second: SXM vs PCIe (2.1), 4x vs 8x (2.5), OEM (3.1), serving stack licensing (4.1), fabric (5.1-5.2)
3 - Blocks deployment | Resolve before go-live: security controls, operations model, governance
P - Parallel track | Lead-time orders (10.3) can proceed once Tier 2 closes, in parallel with Tier 3
How to use
Yellow cells are the only cells to edit: Owner, Required By, Decision / Notes, Status (dropdown: Open / In Progress / Decided / Deferred).
Use the filter row on the Decision Matrix tab to run working sessions by Domain or Tier.
Example row format - Owner: 'J. Smith (CSO AI)', Required By: '2026-08-01', Decision/Notes: '4x H200 SXM confirmed; 70B FP8 primary target'.
Three questions that constrain everything else: largest model x precision x context x concurrency (1.1-1.4); data classification ceiling (7.1); validated kW per rack (8.1).

## Decision Matrix
ID | Domain | Decision Point | Options / Considerations | Why It Matters | Tier | Owner | Required By | Decision / Notes | Status
1.1 | 1. Workload Definition | Target model size(s) | 7B / 14B / 32B / 70B / 100B+ / MoE | Drives GPU count per node, HBM requirement, and whether 4x H200 (564GB HBM) fits one model replica | 1 - Blocks sizing |  |  |  | Open
1.2 | 1. Workload Definition | Precision / quantization policy | BF16/FP16, FP8, INT8, INT4 (AWQ/GPTQ) | FP8 on H200 roughly doubles effective capacity vs BF16; decides how many models fit per node | 1 - Blocks sizing |  |  |  | Open
1.3 | 1. Workload Definition | Maximum context length | 8K / 32K / 128K / 200K+ | KV cache is the hidden memory consumer; 128K contexts at concurrency can exceed the weights' HBM footprint | 1 - Blocks sizing |  |  |  | Open
1.4 | 1. Workload Definition | Concurrent users / sessions | Define P50 / P95 / peak | Determines batch scheduling headroom, tokens/sec targets, and Phase 2 trigger point | 1 - Blocks sizing |  |  |  | Open
1.5 | 1. Workload Definition | Throughput target | Aggregate tokens/sec; per-request tokens/sec | Primary sizing metric for vLLM / TensorRT-LLM benchmarks; validates 4x vs 8x per node | 1 - Blocks sizing |  |  |  | Open
1.6 | 1. Workload Definition | Latency SLA | Time-to-first-token; inter-token latency; total request time | Streaming chat vs batch summarization drive different scheduler and GPU allocation choices | 1 - Blocks sizing |  |  |  | Open
1.7 | 1. Workload Definition | Models resident simultaneously | 1 / 2-4 / model fleet | Multi-model serving may justify MIG partitioning or dedicated nodes per model class | 1 - Blocks sizing |  |  |  | Open
1.8 | 1. Workload Definition | Workload mix | Chat, RAG, agentic tool-calling, embeddings, reranking, batch, fine-tuning | Agentic workloads multiply request volume per user action; fine-tuning changes the platform entirely | 1 - Blocks sizing |  |  |  | Open
1.9 | 1. Workload Definition | RAG scope | Document volume, ingest rate, embedding model, reranker, vector DB choice/placement | Decides whether an auxiliary GPU tier (L40S/L4) offloads embeddings/reranking from H200s | 1 - Blocks sizing |  |  |  | Open
1.10 | 1. Workload Definition | Availability requirement | Pilot / business hours / 24x7 SLA | Drives HA everywhere: firewall pair, redundant ToR, N+1 nodes, backup power | 1 - Blocks sizing |  |  |  | Open
1.11 | 1. Workload Definition | Growth horizon | Single node / rack scale / cluster scale over 12-36 months | Decides whether Phase 1 network and rack choices must already be Phase 3-capable | 1 - Blocks sizing |  |  |  | Open
2.1 | 2. GPU Platform | SXM vs PCIe H200 | SXM (NVLink/NVSwitch, HGX chassis) vs PCIe (cheaper, flexible) | If any single model exceeds one GPU's HBM after quantization, SXM/NVLink is effectively required | 2 - Blocks quoting |  |  |  | Open
2.2 | 2. GPU Platform | GPU tiering | H200 capacity tier only vs H200 + auxiliary L40S/L4 utility tier | Offloading embeddings/rerankers/routing preserves H200 cycles for large-model inference | 2 - Blocks quoting |  |  |  | Open
2.3 | 2. GPU Platform | H200 now vs B200/GB200 later | Buy H200 now; wait for B200; hybrid refresh posture | Allocation lead times vs project urgency; define whether Phase 1 H200s redeploy as utility tier at refresh | 2 - Blocks quoting |  |  |  | Open
2.4 | 2. GPU Platform | GPU partitioning strategy | MIG/vGPU partitioning vs full GPUs with serving-layer isolation | Affects multi-tenancy, chargeback granularity, and driver/licensing choices | 2 - Blocks quoting |  |  |  | Open
2.5 | 2. GPU Platform | 4x vs 8x GPUs per node | 4x (smaller failure domain) vs 8x (max NVLink domain, density) | 8x doubles per-node power/cooling and blast radius on node failure | 2 - Blocks quoting |  |  |  | Open
3.1 | 3. Server Platform & Vendor | OEM selection | Dell XE9680-class / HPE / Lenovo / Supermicro / NVIDIA-certified whitebox | Approved-vendor list, support relationships, BMC fit with DCIM tooling, lead time | 2 - Blocks quoting |  |  |  | Open
3.2 | 3. Server Platform & Vendor | Support contract tier | 4-hr mission critical vs NBD; on-site GPU spares; contract holder | GPUs are the long-lead FRU; contract holder decision (AT&T vs integrator) affects SLA chain | 2 - Blocks quoting |  |  |  | Open
3.3 | 3. Server Platform & Vendor | CPU platform and RAM sizing | AMD EPYC vs Intel Xeon; 1TB vs 2TB ECC | PCIe lane budget for NICs+NVMe and NUMA topology; RAM should follow RAG/preprocessing need, not default to max | 2 - Blocks quoting |  |  |  | Open
3.4 | 3. Server Platform & Vendor | Warranty / lifecycle alignment | 3 vs 5 year | Must align with Phase 3 refresh assumptions | 3 - Blocks deployment |  |  |  | Open
4.1 | 4. Serving & Software Stack | Inference engine | vLLM / TensorRT-LLM / NVIDIA NIM / Triton front-end | NIM requires NVIDIA AI Enterprise (per-GPU per-year licensing) - materially changes TCO; decide early | 2 - Blocks quoting |  |  |  | Open
4.2 | 4. Serving & Software Stack | Orchestration | Bare-metal services (Phase 1) vs Kubernetes day one; which K8s distribution | Alignment with AT&T container platform standards (OpenShift etc.); GPU Operator support | 3 - Blocks deployment |  |  |  | Open
4.3 | 4. Serving & Software Stack | Model registry & artifact management | Registry choice; promotion/rollback workflow; version pinning | Operational control and supply-chain security control (see 7.6) | 3 - Blocks deployment |  |  |  | Open
4.4 | 4. Serving & Software Stack | API gateway / access pattern | OpenAI-compatible surface; rate limiting; per-team keys; quotas | Defines integration contract for consuming teams and metering for chargeback (9.5) | 3 - Blocks deployment |  |  |  | Open
4.5 | 4. Serving & Software Stack | OS / driver baseline & patching | RHEL vs Ubuntu LTS; CUDA/driver pinning; maintenance windows | GPU driver updates are disruptive; define cadence and windows now | 3 - Blocks deployment |  |  |  | Open
4.6 | 4. Serving & Software Stack | User-facing portal | API-only vs Open WebUI vs internal portal; SSO/Entra ID integration | Decides identity integration requirements at day one | 3 - Blocks deployment |  |  |  | Open
5.1 | 5. Network Fabric | Ethernet vs InfiniBand cluster fabric | 100/200GbE RoCE vs InfiniBand | Inference-only usually fits Ethernet and is operationally simpler; IB only if multi-node tensor parallelism or training is in scope. Biggest Phase 2/3 fork | 2 - Blocks quoting |  |  |  | Open
5.2 | 5. Network Fabric | Speed tier per phase | 100GbE Phase 1; 200/400GbE Phase 2+; 400GbE-capable ToR from day one? | Avoids rip-and-replace of Phase 1 switching at Phase 2 | 2 - Blocks quoting |  |  |  | Open
5.3 | 5. Network Fabric | Integration vs standalone fabric | Plug into existing spine/leaf (EVPN/VXLAN) vs isolated pod with controlled uplinks | Governs switch vendor, config standards, and network review timeline | 3 - Blocks deployment |  |  |  | Open
5.4 | 5. Network Fabric | Switch redundancy model | MLAG/redundant ToR from Phase 1 vs accepted single-switch pilot risk | Availability requirement (1.10) flows directly into this | 3 - Blocks deployment |  |  |  | Open
5.5 | 5. Network Fabric | Storage network separation | Shared fabric with QoS vs dedicated storage VLAN/fabric | 70B model pull is 100GB+ per node; decide if it shares the inference path | 3 - Blocks deployment |  |  |  | Open
5.6 | 5. Network Fabric | Switch vendor | AT&T network standards (Cisco-heavy) vs Arista/NVIDIA Spectrum | Approved-vendor fit likely governs | 3 - Blocks deployment |  |  |  | Open
6.1 | 6. Storage & Data | Local-only vs shared storage trigger | Phase 1 local NVMe; define Phase 2 trigger for shared storage | Multi-node model repo, shared vector DB, and corpus growth force the transition | 3 - Blocks deployment |  |  |  | Open
6.2 | 6. Storage & Data | Shared storage class | NFS all-flash vs S3-compatible object vs parallel FS | Inference mostly needs fast sequential reads for model loads; object + local NVMe cache often suffices | 3 - Blocks deployment |  |  |  | Open
6.3 | 6. Storage & Data | Vector DB selection & placement | On GPU nodes vs dedicated VMs vs existing enterprise data platform | Ties into broader data-plane vendor evaluation (lakehouse/analytics platform vs purpose-built vector DB) | 3 - Blocks deployment |  |  |  | Open
6.4 | 6. Storage & Data | Capacity plan (30TB vs 100TB usable) | Enumerate model cache, corpus (raw+chunked), embeddings, log/audit retention | Prompt/completion retention is a legal/compliance decision, not just storage | 3 - Blocks deployment |  |  |  | Open
6.5 | 6. Storage & Data | Backup & DR posture | Backup scope (vector DB, configs, audit logs); RPO/RTO; second-site DR? | Models are re-downloadable; the state around them is not | 3 - Blocks deployment |  |  |  | Open
7.1 | 7. Security & Compliance | Data classification ceiling | Highest classification permitted (customer data? CPNI? regulated data?) | Single answer that drives isolation depth, encryption, audit scope, and review timeline. Likely the longest pole | 1 - Blocks sizing |  |  |  | Open
7.2 | 7. Security & Compliance | Tenant / team isolation model | K8s namespace isolation vs MIG hard partitioning vs separate nodes per tier | Sensitivity tiers may force physical separation | 3 - Blocks deployment |  |  |  | Open
7.3 | 7. Security & Compliance | Encryption requirements | At rest (SED NVMe/array), in transit (TLS, RoCE), confidential computing modes | H200 supports confidential computing; decide if any workload requires it | 3 - Blocks deployment |  |  |  | Open
7.4 | 7. Security & Compliance | NGFW vendor, placement, HA timing | Cisco / Palo Alto / Fortinet / Juniper; pod edge vs east-west; HA at Phase 1 or 2 | Approved-vendor fit governs; placement decides throughput class (10/25/100Gbps) | 3 - Blocks deployment |  |  |  | Open
7.5 | 7. Security & Compliance | Remote access pattern | Jump box / PAM; OEM call-home permissibility | Hardware support workflows depend on this being decided | 3 - Blocks deployment |  |  |  | Open
7.6 | 7. Security & Compliance | AI supply-chain security | Signed model weights, hash validation, image scanning, dependency controls | Treat model artifacts as a supply-chain risk surface with registry-level provenance attestation | 3 - Blocks deployment |  |  |  | Open
7.7 | 7. Security & Compliance | Agentic-workload guardrails | Per-agent rate limits, tool-call logging, prompt/response audit, ATLAS/OWASP-aligned telemetry | Defines what the platform must emit to the SIEM to support agent-behavior detection | 3 - Blocks deployment |  |  |  | Open
7.8 | 7. Security & Compliance | SIEM integration scope | Infra logs only vs inference-layer events (authN, prompt metadata, model version, anomalies) | Log volume and retention costs follow directly | 3 - Blocks deployment |  |  |  | Open
7.9 | 7. Security & Compliance | Vulnerability management ownership | Who patches GPU drivers, CUDA, serving-stack CVEs, on what SLA | vLLM and adjacent projects move fast and have had real CVEs | 3 - Blocks deployment |  |  |  | Open
8.1 | 8. Facilities: Rack / Power / Cooling | Power budget per node and per rack | 4x H200 PCIe ~4-6kW; 8x H200 SXM ~10-12kW; nodes per rack vs available kW | Facility power frequently caps the design before budget does | 1 - Blocks sizing |  |  |  | Open
8.2 | 8. Facilities: Rack / Power / Cooling | Air vs liquid cooling | Air (4x nodes, proper hot/cold aisle) vs rear-door HX / DLC (8x SXM density) | Get facility's validated per-rack cooling capacity in writing before selecting node density | 1 - Blocks sizing |  |  |  | Open
8.3 | 8. Facilities: Rack / Power / Cooling | Facility selection | Existing AT&T DC vs colo vs lab space for Phase 1 | Power/cooling/security review timelines differ; often the schedule-critical path | 1 - Blocks sizing |  |  |  | Open
8.4 | 8. Facilities: Rack / Power / Cooling | Power protection & PDU spec | Facility UPS/generator vs in-rack UPS; A/B feeds; 30A/60A single vs three-phase | PDU amperage must match node PSUs; A/B feed availability drives redundancy design | 3 - Blocks deployment |  |  |  | Open
8.5 | 8. Facilities: Rack / Power / Cooling | Physical security & smart hands | Badge access model, camera coverage, remote-hands provider | Operational dependency for a lights-out GPU pod | 3 - Blocks deployment |  |  |  | Open
9.1 | 9. Operations & Service Model | Operating ownership (RACI) | AT&T infra / CSO AI team / integrator / hybrid across 4 layers (HW, OS, serving, model) | Four layers often mean four different owners; unclear RACI stalls production readiness | 3 - Blocks deployment |  |  |  | Open
9.2 | 9. Operations & Service Model | SLA definition & on-call | Measured on API availability? latency percentiles? On-call rotation; OEM/NVIDIA escalation | Phase 3 promises SLA-backed service; define measurement now | 3 - Blocks deployment |  |  |  | Open
9.3 | 9. Operations & Service Model | Observability stack & alerting | Prometheus/Grafana + DCGM vs enterprise monitoring standard; alert thresholds and recipients | GPU temp, HBM ECC errors, KV cache pressure, queue depth need owners | 3 - Blocks deployment |  |  |  | Open
9.4 | 9. Operations & Service Model | Capacity management & Phase 2 trigger | Metric thresholds (e.g., sustained >70% GPU util at P95, SLA breaches) and decision owner | Turns 'scale later' into a governed, budgetable event | 3 - Blocks deployment |  |  |  | Open
9.5 | 9. Operations & Service Model | Chargeback / showback model | Per-token, per-GPU-hour, per-team allocation; metering via API gateway | Required by Phase 3; metering design should exist by Phase 1 | 3 - Blocks deployment |  |  |  | Open
9.6 | 9. Operations & Service Model | Change management | Model promotion, driver updates, serving upgrades through AT&T change control | Define maintenance windows and rollback procedures | 3 - Blocks deployment |  |  |  | Open
10.1 | 10. Procurement & Financial | CapEx vs OpEx model | Purchase vs lease vs OEM as-a-service (APEX / GreenLake class) | Also decide whether cloud/GPU-cloud alternative needs a formal TCO comparison | 3 - Blocks deployment |  |  |  | Open
10.2 | 10. Procurement & Financial | TCO model scope & baseline | HW + AI Enterprise licensing + support + power (~$10-15K/yr per 10kW node) + facility + staffing | Define comparison baseline (API models, cloud GPU rental) and the utilization assumption that makes on-prem win | 3 - Blocks deployment |  |  |  | Open
10.3 | 10. Procurement & Financial | Lead-time management | H200 systems can carry multi-month lead times; order timing vs facility readiness; interim node? | Can be placed once Tier-2 decisions close, in parallel with Tier-3 items | P - Parallel track |  |  |  | Open
10.4 | 10. Procurement & Financial | Budget phasing & approval gates | What Phase 1 must demonstrate (benchmarks, adoption, cost-per-token) to unlock Phase 2 | Write exit criteria before hardware arrives | 3 - Blocks deployment |  |  |  | Open
10.5 | 10. Procurement & Financial | Vendor consolidation | Single-integrator turnkey vs component procurement via existing supplier agreements | Affects accountability chain and pricing leverage | 3 - Blocks deployment |  |  |  | Open
11.1 | 11. Governance & Program | Model governance | Approved model list (license review: Llama, Qwen, Mistral, etc.); approval workflow; gateway enforcement | Open-weight license terms require legal review before production use | 3 - Blocks deployment |  |  |  | Open
11.2 | 11. Governance & Program | Acceptable use & data handling policy | What users may submit; prompt/response retention; privacy posture; legal review | Retention of completions is a compliance decision | 3 - Blocks deployment |  |  |  | Open
11.3 | 11. Governance & Program | Pilot success metrics | Target benchmark (e.g., 70B FP8 at N users under X ms TTFT); adoption; cost per M tokens vs API | Define before hardware arrives so Phase 2 has an objective gate | 3 - Blocks deployment |  |  |  | Open
11.4 | 11. Governance & Program | Decision owners & deadlines | Assign owner + required-by date to every open row in this matrix | Unowned decisions default to the most expensive answer | 1 - Blocks sizing |  |  |  | Open